## Slide 1
ESO Digital Ways of Working – Stakeholder Engagement & Communications Plan
Deliverable no. 2 in Phase 1: Discover
June 2021

## Slide 2: Walk Me A brief summary on how to use this document
Purpose: The purpose of this document is to provide a summary of the Engagement and Communications needs of the 16 week PwC support, as part of the NG ESO Digital Ways of Working programme. For completeness, we have integrated the central communications plan developed by Debbie Milsom as part 2.
Audience: Core ESO Digital Ways of Working programme team members, specifically the Business Change and Communication representatives (in particular, Debbie Milsom as the Digital Ways of Working Communications Lead).
Intended Use: This document is intended to provide a summary of the detailed engagement and communications plan here. It will be delivered by Debbie Milsom (Digital Ways of Working Communications Lead), with support as requested.
Inputs: To create this document we have utilised the Stakeholder Analysis produced for the programme, the NG ESO communications channels, the ESO Technology communications channels and the planned communications channels for the Digital Ways of Working programme.

## Slide 3
Contents Table
What’s included in this document?
Page | Section |  | Description | Link
Part 1 |  |  |  | 
5 | Introduction | Introduction | An introduction to this document, including some upfront recommendations on communications collateral required. | here
6 | Our Summary Engagement and Communications Plan | Our Summary Engagement and Communications Plan | A plan on a page articulating the key engagement and communications over the 16 week PwC support period. | here
7 - 9 | Detail for each Engagement and Communications ‘event’ | Detail for each Engagement and Communications ‘event’ | An articulation of the purpose behind each engagement and communication activity recommended. | here
10 - 13 | Integrated plan on a page | Integrated plan on a page | A overall summary of events for the culture and change workstream | here
14 | Leadership Cascade template | Leadership Cascade template | A useful one pager for the NG ESO Technology Leadership to cascade key programme messages to their teams. | here
15 | Suggested Future Engagement and Communications | Suggested Future Engagement and Communications | An overview of other engagement and communication channels to utilise following the 16 week PwC support Period. | here
Part 2 |  |  |  | 
16 - 34 | ESO Technology Communications Plan | ESO Technology Communications Plan | Existing plan, developed by Debbie Milsom and Stefan D’Alessandro. | here

## Slide 4: Part 1 – Digital Ways of Working Engagement and Communications Plan

## Slide 5: Introduction The National Grid ESO Engagement and Communications plan for the Digital WoWing Programme
The purpose of an Engagement and Communications plan is to detail the activity required to engage our stakeholders and help move them along the change commitment curve, as established by their current perspective on change, the level of impact and their required role. This information is detailed in the stakeholder analysis here. This document therefore provides a high level overview of these requirements and is supported by the excel engagement and communications plan here, which will be delivered Debbie Milsom, the Digital Ways of Working Communications Lead.
In addition to the below engagement and communications articulated, we strongly suggest that a core set of communications collateral is developed to provide a single source of the truth for the programme, to which all communications can be based. This could include:
Commitment
High
Ownership
Time Horizon
Readiness
Low
Current
Vision Achieved
Acceptance & Engagement
Understanding
Awareness
an overall transformation narrative (including the vision, case for change, benefits and overall roadmap)
an extension of the key messages, tailored for each stakeholder group
an elevator pitch for leaders in the business, to ensure they are able to articulate the transformation narrative in brief and in a way that is relevant to their business area
a ‘what does this mean for me? / Day in the Life of…’ view against key stakeholder groups
a set of Frequently Asked Questions
NB. These could be done in a variety of mediums including PowerPoint, infographics and video.
Finally, we recommend that the Digital WoWing stakeholder list (which makes up the ‘WoWing group’ noted on the following slide) is reviewed to ensure it is extended to include all impacted stakeholders, not just representatives from the impacted business areas.

## Slide 6: Introduction Key Messages to use in all Communications
To ensure that all engagement and communications reinforce the central tenants of the programme, draw from a single source of the truth and are consistent, the following key messages should be utilised.
Key words include: customer-centric, collaboration, communication, accountability, openness.
National Grid ESO embrace being able to operate a zero-carbon system by 2025, using this to provide even greater value for consumers. An ambitious target, which is also set within the context of delivering against RIIO-2, the new control period set by Ofgem in April 2021 to run for five years.
This has created an imperative for NG ESO to transform, through adopting a new ways of working that embraces collaborative and seamless working cross functions. This will focus on transitioning from a project to a product focused model, refining the supporting customer journeys and adopting Scaled Agile For enterprise (SAFe).
Our vision is to unite Business Operations and Technology to deliver customer-centric digital products that enable our customers success.
To make this a success, we need our Business Operations and ESO Technology to work together collaboratively and iteratively in a one-team TechOps mindset, as well as placing the customer firmly in the product development lifecycle.
Through this transformation, we will: Improve customer satisfaction scores, Increase the speed of idea to product, Leverage diversity of thought to produce higher quality outcomes
Digital Ways of Working is the foundation to accelerating ESOs overall success. It is a three-to-five-year journey in which we all an important role, so fully immerse yourself in the programme and take charge of how your role plays its part.

## Slide 7: Summary Engagement and Communications How we will do over the next 16 weeks….
 | Discover |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Define |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | Construct |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | Review |  |  |  |  |  |  |  |  |  | 
 | wc 17/05 | wc 24/05 | wc 31/05 | wc 07/06 | wc 14/06 | wc 21/06 | wc 28/06 | wc 05/07 | wc 12/07 | wc 19/07 | wc 26/07 | wc 02/08 | wc 09/08 | wc 16/08 | wc 23/08 | wc 30/08 | Wc 06/08
Reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Exec. / Tech. Leadership |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG ESO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ESO Tech. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
.WoWing Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Product WoWing . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Customer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Culture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Initial Findings Report
Draft Report
Final Report
Norma Dove-Edwin Led
WoWing Deliverable
ESO WoW Weekly Comms Culture Survey ‘Heads Up’
Focus Group Invites
Baseline Results and Sprint Kick Offs
During Sprint comms tbc.
Focus Groups
Invitation to Complete Survey & Reminder Comms
Focus Group Follow Up Comms
Change Champs Engagement
Validating CIA
Invitation to Complete CRA and Reminder Comms
Invitation to Complete CCA and Reminder Comms
CRA prime
CCA prime
Kick Off
All Hands
All Hands
All Hands
All Hands
Date tbc / tbc with CA
Grid: Home Celebrating Success
All Hands
Date tbc / tbc with CA
Grid: Home Celebrating Success
NL
Weekly Newsletter
NL
NL
NL
NL
NL
NL
NL
NL
NL
NL
NL
NL
Shout IT out
Shout IT out
NN
Norma’s Note
NN
NN
NN
NN
NN
NN
Technology Leadership Monthly
Teams Cascade
Technology Leadership Monthly
Teams Cascade
Technology Leadership Monthly
Teams Cascade
Focus Groups
Focus Groups
Focus Groups
Focus Groups
ESO ET
ESO ET
ESO ET
Primer Comms in Weekly NL
Primer Comms in Weekly NL
Teams Cascade
Corporate Affairs Led
Teams Cascade
Teams Cascade
NB. As required, engagement should extend to leadership teams from across the business, as directed by the ESO ET
WoWing Wednesday’s – key messages on MS teams
KM
KM
KM
KM
KM
KM
KM
KM
KM
KM
CRA Leadership prime
CCA Leadership prime
Day in the Life of videos

## Slide 8: Summary Engagement and Communications Overview of each planned engagement / communication (1/2)
To provide further detail against the above articulated 16-week plan, the below table describes each ‘event’ in turn.
Stakeholder Group | Planned Engagement & Communications | Purpose | Cadence / Date | Content Owner | Delivery Owner
ESO Exec & Technology Leadership | ESO ET | Leadership alignment to discuss strategic priorities, share relevant updates, outline key issues identified across ESO business areas and make decisions. In addition, working together to agree actions the executive can take to support the success of the programme. Use as a vehicle to cascade locally. | Weekly | DM & ND-E | ND-E
 | ES Technology Leadership | Share programme updates and drive collaborative problem solving for Digital WoWing. Use as a vehicle to cascade information locally. | Monthly | DM & ND-E | ND-E
NG ESO | All Hands | To reach all of the organistion and drive a baseline level of knowledge for the programme. In addition, to provide the opportunity for two-way discussion and keep everyone informed of progress / opportunities to get involved. | Monthly | DM | ND-E
 | Grid: Home Celebrating Success | Share success and provide updates in relation to the WoWing programme | Monthly | DM | ND-E
 | Yammer | Ad hoc sharing of success to whole organisation, as and when Digital WoWing programme requires. | Ad hoc | DM | ND-E
ESO Technology | Norma’s Note | Blog style note from Norma covering both business and personal journey, to include regular representation of the Digital WoWing. | Bi-Weekly | DM | ND-E
 | Shout IT out | Highlight ESO Technology success and value-added, in a more informal environment. Ensure the appropriate promotion is used, such as the @mention functionality. | Ad-hoc | DM | ND-E
WoWing Group | Weekly Newsletter | To share a timely view on programme updates, successes, upcoming events and milestones. | Weekly | DM | ND-E
 | WoWing Wednesday’s | To share a bitesize view of the weekly newsletter, using three key take away’s. | Weekly | DM | ND-E
 | All Hands | To reach the most impacted stakeholders and drive a detailed understanding for the programme. In addition, to provide the opportunity for two-way discussion and keep everyone informed of progress / opportunities to get involved. | Monthly | DM | ND-E
Product WoWing Stakeholders | Focus Groups Priming Comms | To prime ESO that the focus groups are coming, in terms of purpose and importance of their collaboration. | 18/06/21 | DM | ND-E
 | Focus Groups | Collaborate on the development of the Project Ways of Working Model Journeys to ensure business relevance. | wc 28/06/21 – 05/07/21 | JO | JO
Customer Journeys Stakeholder | Focus Groups Priming Comms | To prime ESO that the focus groups are coming, in terms of purpose and importance of their collaboration. | 18/06/21 | DM | ND-E
 | Focus Groups | Collaborate on the development of the Customer Journeys to ensure business relevance. | wc 28/06/21 – 05/07/21 | PJ | PJ
Product WoWing & Customer Journets | Day in the Life of Videos | Develop 3+ engaging videos (approx. 2-3 minutes in length), to bring to life the key changes associated with the product ways of working and the customer journeys. This will be put into the context of key persona’s to help answer the question ‘what does this mean for me? | Wc 06/08/21 | EN / PJ / JO | ND-E
NB. Initials refer to Norma Dove-Edwin, Debbie Milson, Prash Joshi and Jimmy Oppong.

## Slide 9: Summary Engagement and Communications Overview of each planned engagement / communication (2/2)
To provide further detail against the above articulated 16-week plan, the below table describes each ‘event’ in turn.
Stakeholder Group | Planned Engagement & Communications | Purpose | Cadence | Content Owner | Delivery Owner
Culture | ESO WoW Weekly Comms Culture Survey ‘Heads Up | To prime ESO that the survey is coming, in terms of purpose and importance of their collaboration. | 28/05/21 | DM | ND-E
 | Invitation to Complete Survey & Reminder Comms | To request collaboration on the survey and drive up response rate. | 09/05/21 | DM | ND-E
 | Focus Group Invites | To prime invitees of the session, their importance in the process and what is covered in the session to help guide thinking beforehand. | 21/06/21 | EN | AB
 | Focus Groups | To playback the Culture Thumbprint survey results to see if they resonate in participants business areas, explore the behaviours displayed in correspondence with the dominant cultural traits and discuss what behaviours are critical to building on cultural strengths. | wc 28/06/21 | EN | EN
 | Focus Group Follow Up Comms | To share the outcomes of the focus groups and recap next steps. | 09/07/21 | EN | EN
 | Change Champs Engagement | To mobilise the change champion network, as a key vehicle for the behavioural sprint. | wc 19/07/21 | EN | AK
 | Baseline Results and Sprint KO | To share the outcomes of the Culture Thumbprint survey to impacted stakeholders, articulate what this means for how we would like to evolve the culture as well as what their role is within the journey. | wc 02/08/21 | EN | ND-E
 | During Sprint comms tbc. | To keep momentum and obtain feedback on how the behavioural tweaks / nudges are landing. | tbc | EN & DM | ND-E
Change | CRA Leadership Prime | To prime ESO leadership that the survey is coming, in terms of purpose, importance of their collaboration and how they can drive response rate in their teams. | wc 28/06/21 | EN & DM | ND-E
 | CRA Prime | To prime ESO that the survey is coming, in terms of purpose and importance of their collaboration | wc 05/07/21 | DM | ND-E
 | Invitation to Complete CRA and Reminder Comms | To request collaboration on the survey and drive up response rate. | wc 12/07/21 | DM | ND-E
 | Validating CIA | To ensure that the change impact assessment reflects the ESO business accurately, particularly around the ‘as-is’ state. | wc 02/08/21 | EN | EN
 | CCA Leadership Prime | To prime ESO leadership that the survey is coming, in terms of purpose, importance of their collaboration and how they can drive response rate in their teams. | wc 02/08/21 | EN & DM | ND-E
 | CCA Primer | To prime ESO that the survey is coming, in terms of purpose and importance of their collaboration | wc 09/08/21 | DM | ND-E
 | Invitation to Complete CCA and Reminder Comms | To request collaboration on the survey and drive up response date. | wc 16/08/21 | DM | ND-E
NB. Initials refer to Norma Dove-Edwin, Debbie Milsom, Alex Knight, Adam Bartlett and Emily Novakovic.

## Slide 10: ESO/PwC Digital Ways of Working (WoW) Change & Culture Workstream Deliverables Plan on a Page

## Slide 11
05th July
08th July
09th July
12th July
14th July
15th July
Briefing with senior management on the up and coming CRA, baseline results, CAP and BS
Culture
Baseline Report Issued
Send CRA chaser to respondents
Change champion kick off event
Workshop culture baseline and action plan
Send CRA chaser to Leadership asking cascade to respondents
Change readiness assessment survey to be issued by Norma
Culture Baseline Issue results / finding for ESOT pre-read
ESOET
15th July
Meeting
Deliverable/Work product
Communications

## Slide 12
16th July
19th July
23rd July
03rd Aug
06th Aug
09th Aug
CRA closure comms
Culture Action plan (CAP) delivered
Early review of draft CAP with Norma & Rob
Briefing with senior management on the up and coming CCA (change commitment assessment)
Pending CIA Behavioural sprint (BS)
TBC
Aug CIA Deliverable
TBC
Meeting
Deliverable/Work product
Communications

## Slide 13
16th Aug
18th Aug
19th Aug
20th Aug
CCA Launch Comms
CCA chaser to management asking to cascade to respondents
CCA respondents chaser
CCA closure comms
Change Action Plan
TBC
Behavioural sprint comms TBC (2 weeks in)
TBC
Capability & Training plan
TBC
Meeting
Deliverable/Work product
Communications

## Slide 14: Leadership Cascade Useful support template….
[insert key message to be cascaded]
2
[insert key message to be cascaded]
3
[insert key message to be cascaded]
4
[insert key message to be cascaded]
5
[insert key message to be cascaded]
1
So what does this mean for us?
[to be populated by ESO Tecnhology Leadership, for their area of the business]

## Slide 15: Summary Engagement and Communications Recommendations post PwC 16 week support….
Given the previous Engagement and Communications plan represents only a small part of the overall Digital Ways of Working journey that NG ESO will go on, the below shares some activity to consider going forward.
In line with 1:1 with Fintan Slye
To provide the opportunity for questions, a two way dialogue and access to leadership
Delivered virtually, with either only Norma or rotating hosts
To follow the roadshow timeline
1:1 with Norma / Transformation Drop-ins
What is the objective?
To further drive publicity and raise awareness across the whole of NG ESO
To increase leadership visibility and active sponsorship
Driven though WoWing Newsletter
Leadership Talking Heads
What is the objective?
Once to ‘to be’ state is known circulate around business areas to share this and the transition plan.
To drive publicity and raise awareness across the whole of NG ESO
Phased roll out, targeting the most impacted populations first
Transformation Roadshow
What is the objective?
Network of individuals across the business to help accelerate adoption of the new ways of working
Supporting both onward cascade, business feedback and ways of working changes
Change Network
What is the objective?
To reinforce customer focus, as driven by programme
A subset of existing NG ESO to be selected
An opportunity for NG ESO to obtain external insight to stretch ambition, accelerate the programme and ensure seamless collaboration
Customer Advisory Board
What is the objective?
To reinforce collaboration, as driven by programme
A subset of business areas to be selected as representatives (both formal and informal leaders)
An opportunity for NG ESO to solve the common challenges together and allowing for transparency in decision making.
Cross Functional Design Forum
What is the objective?

## Slide 16: Part 2 – ESO Technology Communications Plan

## Slide 17: ESO Technology Communications Plan
This plan identifies our key stakeholders and their communications needs
We group stakeholders into categories based on their interest and influence
It identifies the key communication channels and timelines
The plan includes deliverables for ESO Technology & the WoW Project

## Slide 18: Stakeholder engagement approach
Partnership
Joint planning, joint campaigns/press, joint research
Involvement
Open forums, round-table discussions, working groups, seminars, user panels, conferences.
Commitment and understanding
Focus groups, task groups, visits, deliberative meetings, data sharing, call for evidence
Awareness
newsletters, websites, speeches, emails, press releases
Less effort more stakeholders
Greater effort fewer stakeholders
Low influence
High interest
High influence
Low interest
High influence
High interest
Low influence
Low interest
Engage
Keep satisfied
Consult
Inform

## Slide 19: ECO Ways of Working
PARTNERSHIP
Operations and Technology working with a one-team mindset. Committed to seeing the journey through to fruition.
Working together for mutual gain, in the best interests of the customer.
DIGITAL MINDSET
Striving for innovation and faster delivery. Delivering digital customer solutions first.
PRODUCT MODEL
Focusing on outcomes and continues improvement.
Simplifying/standardising our products for customers to easily understand the offering.
AGILE DELIVERY
Focused on solution and delivery.
Continually building and releasing customer focused products.
MULTIDISCIPLINARY TEAMS
Frequent, relevant and tailored communications.
Improving collaboration across disciplines to deliver in the best interests of the customer.
CULTURE AND BEHAVIOURS
Encouraging open knowledge sharing. Empowering individuals to take accountability. Embracing inclusion.
Changing the way we behave to deliver a customer centric culture.
ESO INTEGRATED PORTFOLIO BACKING
Lean governance.
Better understanding of customers.
Co-ordinated portfolios across ESO to meet its business goals.
CUSTOMER CENTRIC

## Slide 20
Awareness
Provide timely, target Communications using appropriate Channels to engage, inspire and create awareness of the journey, the objectives and the roles individuals and teams play
Understanding
Using Channels such as Lunch & Learns or hosting Guest Speakers, we will ensure there is a better level of understanding
Readiness
User Engagement/Adoption
Keeping users and key stakeholders engaged via relevant messaging
Use of case studies which demonstrate success
Providing roadmaps
Regular check-in to ensure the desired level of understanding has been achieved

## Slide 21
We want to focus on the customer and improve our satisfaction scores by delivering valued products and services. ​
We need our business operations and ESO Technology to operate with a one-team TechOps mindset​
This will enable us to reduce the time between idea and product and include the customer in the product development lifecycle.​
‘Ways of Working’ will build the foundation to accelerate our journey – and it is a journey.​
We all need to immerse ourselves in WoW and drive the change…and not be driven by it!
WoW Key Messages

## Slide 22: Stakeholders
Approach | Stakeholder group | 
Partnership Engage | ESO IT team Directly impacted ITLT (Narayan, Shannon) IT delivery centres (SE, I&O, CNI) Ofgem RIIO-2 transformation team Finance | ESO Band Bs Band C portfolio owners Product managers/owners ESO business change ESO business architecture
Involvement Keep satisfied | Indirectly impacted ITLT (Orla Daily) IT Digital IT leadership (George Anderson, Tony Rook) Technology advisory council | BEIS ERSG ESO Board
Commitment and understanding Consult | ATO ESO commercial team HR Procurement | Elexon External key stakeholders (e.g. Joanna Hubbard) ADAM partners
Awareness Inform | IT commercial IT EPMO | TSOs RSCs ENTSO-E

## Slide 23
FROM PROJECT FOCUSED
We gravitate towards ‘independent’ project working
We have a closed culture and guarded behaviours
Everyone in the team will commit to work together towards a single
goal and business plan
We want to stick to the plan, making course correction difficult
We rely too much on the Waterfall methodology
We will track, measure and drive continuous improvement
We will have a simple, lean governance structure
We will promote a culture of open knowledge sharing and behaviours
We will focus on innovation and speed of delivery
We don’t want to make decisions - we prefer to escalate
We want to stick to the plan, making course correction difficult
We will have a single view of our Customers
We will focus on an integrated, big picture view
Our Business operations and Technology teams work in silo
Our governance is bureaucratic
INFOGRAPHIC
TEMPLATE
CUSTOMER
We will collaborate and operate as multidisciplinary teams
TO PRODUCT FOCUSED

## Slide 24: ESO IT team communications plan
Communications with the ESO IT team will be fun and engaging.
 |  | 1. Awareness | 2. Understanding | 3. Readiness | 4. Adoption | 5. Rev-evolution
Digital mindset | Customer experience journey |  | Guest speaker | Guest speaker | Guest speaker | Guest speaker
 | Culture and behaviours |  | Who we want to be Survey*r | Positive reinforcement Team examples | Positive reinforcement Team examples | Positive reinforcement Team examples
 | Communication and engagement |  | What is enablement High level plan update*r |  |  | 
Product model | Ways of working (WoW) | All hands meetings | Architecture runway | WoW walk through Team process deep dives Platform deep dives Roadmaps | Teams demo successes | 
 | Capability and training matrix |  |  |  |  | 
Agile | Scaled agile |  | SAFe training |  |  | 
– From and to colleague experience stage
*r – recurring process

## Slide 25: Fun and Engaging Ideas
Concept: Thank you Thursdays
Frequency: Thursdays
Content: Ask: Nominate teams or individuals who have gone above and beyond, lived and breathed the values, or demonstrated exceptional Customer focused thinking or behaviours. Recognition emails sent to nominees; further recognition on relevant calls and nominees mentioned in monthly Newsletter (see below) Option to provide an award/voucher?

## Slide 26: Fun and Engaging Ideas
Concept: shout IT out!
Frequency: As and when
Content: Chance to showcase great work teams/individuals have done. Could be shared via creating a infographic, or short video and will feature pics/quotes from the relevant teams/individuals. Could also be shared more widely across the Business (on the intranet or in ESO wide newsletters etc)

## Slide 27: Fun and Engaging Ideas
Concept: bits and bITes Newsletter
Frequency: Monthly
Content: Interview with 1 or 2 people; Dates for your diary; Priorities/Focus look forward; Successes/Wins look back; 5 fun facts collation; Thank you Thursday roundup; crosswords / quiz (chance to win spot prizes?); various pictures

## Slide 28: Fun and Engaging Ideas
Concept: Ways of Working Wednesday
Frequency: Wednesdays
Content: To share snippets/bite sized chunks of information/quotes/statistics relating to WoW to defined stakeholder group. Email & Teams.

## Slide 29: Fun and Engaging Ideas
Concept: Norma’s Note
Channel: Teams
Frequency: Bi-Weekly/TBC
Content: Personal note (blog style) looking at priorities, journey to date, key deliverables etc. To include thoughts on your personal journey, what books you are currently reading etc 😊

## Slide 30: Fun and Engaging Ideas
Concept: 5 Fun Facts Friday
Frequency: Friday
Content: To share 5 fun facts about places, people, colleagues, animals – anything! Idea is to then nominate a colleague at the end of the fact sharing to provide the following week’s 5 fun facts (like passing a baton)

## Slide 31: Existing Channels
Teams Channels
Email
Project Meetings
ESO Newsletter
All Hands
Teach In
ESO Grid Home
Yammer
Change Champions Network

## Slide 32: Available Channels
In order to achieve the communications objectives, the key messages should be communicated via a number of existing and new communications channels. The proposed activities below will complement the existing channels.
.
Create & publicise the ‘Journey to Live’ map
Creative and Fun Ideas
Animations (infographics/Whiteboard/Video) explaining complicated processes in a simple easy to understand language
Communications materials to support stakeholder engagement programme and high level meetings
Lunch & Learn Sessions

## Slide 33: Measuring Communications Effectiveness